## Sheet1
| ID | User Stories | Priorities | Success Scenarios | Failure Scenarios | Comments | Assigned | Finished
Visitor | 1.1 | As a visitor, I can sign up/register as a user so that I can create an account. | High | the visitor is redirected to the last page he/she was on before registering. | • Visitor does not provide any of the required fields. • Visitor enters an already existing e-mail address • Passwords do not match |  | youmna
| 1.2 | As a visitor, I can browse the site and view the information on it. | high | The view-summary page is retrieved displayed. |  | all controllers not signed in have the same view. | islam
| 1.3 | As a visitor, I can be able to check the information of the activities, so that I can decide which activity fits me more. | high | The business place page is retrieved and viewed | - | Both client and visitor have the same view, although a visitor is not logged in. | Sara
| 1.4 | As a visitor, I can filter the results so that I can select what I want. | medium | Search results are retrieved and displayed. | No results. An appropriate message is viewed. | Both client and visitor have the same view, although a visitor is not logged in. | Islam(backend)-youmna(backend)
| 1.5 | As a visitor, I can view the special offers of activities so that I can benefit from them. | low | A list of all offers is retrieved and shown. | No offers exist. Relevant message is displayed. | Both client and visitor have the same view, although a visitor is not logged in. | Islam
| 1.6 | As a visitor , I can view cinema's reviews to be able to decide which one is suitable. | medium | Detailed reviews are fetched and viewed | No reviews exist. Empty page. | Both client and visitor have the same view, although a visitor is not logged in. | Youmna
| 1.7 | As a visitor , I can view concert's reviews to be able to decide which one is suitable. | medium | Detailed reviews are fetched and viewed | No reviews exist. Empty page. | Both client and visitor have the same view, although a visitor is not logged in. | Youmna
| 1.8 | As a visitor , I can view escaperoom's reviews to be able to decide which one is suitable. | medium | Detailed reviews are fetched and viewed | No reviews exist. Empty page. | Both client and visitor have the same view, although a visitor is not logged in. | Youmna
| 1.9 | As a visitor , I can view fight's reviews to be able to decide which one is suitable. | medium | Detailed reviews are fetched and viewed | No reviews exist. Empty page. | Both client and visitor have the same view, although a visitor is not logged in. | Youmna
| 1.1 | As a visitor , I can view kora's reviews to be able to decide which one is suitable. | medium | Detailed reviews are fetched and viewed | No reviews exist. Empty page. | Both client and visitor have the same view, although a visitor is not logged in. | Youmna
| 1.11 | As a visitor , I can view malahy's reviews to be able to decide which one is suitable. | medium | Detailed reviews are fetched and viewed | No reviews exist. Empty page. | Both client and visitor have the same view, although a visitor is not logged in. | Youmna
| 1.12 | As a visitor , I can view race's reviews to be able to decide which one is suitable. | medium | Detailed reviews are fetched and viewed | No reviews exist. Empty page. | Both client and visitor have the same view, although a visitor is not logged in. | Youmna
| 1.13 | As a visitor , I can view theater's reviews to be able to decide which one is suitable. | medium | Detailed reviews are fetched and viewed | No reviews exist. Empty page. | Both client and visitor have the same view, although a visitor is not logged in. | Youmna
| 1.14 | As a visitor , I can view trampoline's reviews to be able to decide which one is suitable. | medium | Detailed reviews are fetched and viewed | No reviews exist. Empty page. | Both client and visitor have the same view, although a visitor is not logged in. | Youmna
User | 2.1 | As a user I want to sign in So that I can access my page. | high | User is redirected to the last page he/she was on before log in. | • Unregistered e-mail • Password does not match provided e-mail • User is blocked. | • client,service provider and Admin have the same view. • In all mentioned exceptions, a relevant error message is displayed verifying the exact problem and login is unsuccessful. | Youmna
| 2.2 | As a user I want to choose a place (eg: breakout, battle field, paintball, bubble football, cinemas, etc...) So, that I can access any place information. | high | The view-summary page is retrieved displayed. | · No places to show. Error message displayed. | Both client and visitor have the same view, although a visitor is not logged in. | rana
| 2.3 | As a user I want to see every place's Business information (Name, Location) | high | The business place page is retrieved and viewed |  | Both client and visitor have the same view, although a visitor is not logged in. | Sara
| 2.4 | As a user I want to view the cinema category with it's timings to be able to book. | high | the ctegory info is retrieved and viewed |  |  | kareem
| 2.5 | As a user I want to view the concert category with it's timings to be able to book. | high | the ctegory info is retrieved and viewed |  |  | kareem
| 2.6 | As a user I want to view the escaperoom category with it's timings to be able to book. | high | the ctegory info is retrieved and viewed |  |  | kareem
| 2.7 | As a user I want to view the fight category with it's timings to be able to book. | high | the ctegory info is retrieved and viewed |  |  | kareem
| 2.8 | As a user I want to view the kora category with it's timings to be able to book. | high | the ctegory info is retrieved and viewed |  |  | kareem
| 2.9 | As a user I want to view the malahy category with it's timings to be able to book. | high | the ctegory info is retrieved and viewed |  |  | kareem
| 2.1 | As a user I want to view the theater category with it's timings to be able to book. | high | the ctegory info is retrieved and viewed |  |  | kareem
| 2.11 | As a user I want to view the trampoline category with it's timings to be able to book. | high | the ctegory info is retrieved and viewed |  |  | kareem
| 2.12 | As a user I want to view the race category with it's timings to be able to book. | high | the ctegory info is retrieved and viewed |  |  | kareem
| 2.13 | As a user I can filter the business Places by the location (Drop Down), Type, and/or Name So that I can see the places that fit my criteria. | low | Search results are retrieved and displayed. | No results. An appropriate message is viewed. | Both client and visitor have the same view, although a visitor is not logged in. | Islam(backend)-youmna(backend)
| 2.14 | As a user I want to check every place available offers So that I can benefit from them. | low | A list of all offers is retrieved and shown. | No offers exist. Relevant message is displayed. | Both client and visitor have the same view, although a visitor is not logged in. | Islam
| 2.15 | As a User, I can view the reviews posted by any user So that I can know every user thoughts. | medium | Detailed reviews are fetched and viewed | No reviews exist. Appropriate message is displayed. | Both client and visitor have the same view, although a visitor is not logged in. | youmna
| 2.16 | As a User I want to sign out So that I can leave my page. | low | User is redirected to the directory page | - | - | youmna
| 2.17 | As a User I want to update my profile (name, Password, home location (Drop Down), Payment Method, Phone number, contact method) So that I can change a specific attribute. | medium | A message confirming successful update and database is updated. | old info apears if nothing is updated |  | nour
| 2.18 | As a User I want to see the schedule timing of every place So that I can know which slots are free to book there. | high | The business place page is retrieved and viewed |  |  | kareem
| 2.19 | As a User I want to check prices of the places with their timings So that I can decide to book or not. | high | The business place page is retrieved and viewed |  |  | kareem
| 2.2 | As a User I want to book a place in any entertainment with a specific time So that I can benefit from my booking. | high | A confirmation message appears, and a confirmation message with all the details is sent to the e-mail/phone of the user according to the chosen contact method. | • No time slot is chosen. | In all mentioned exceptions, a relevant error message is displayed verifying the exact problem and booking is unsuccessful. | kareem
| 2.21 | As a User I must have the option to pay by credit card or cash so that I can purchase my booking. | high | Upon the payment method (credit card, cash) the system will redirect the user to the payment method procedure | No choosen method to pay with. |  | kareem
| 2.22 | As a User I can cancel my booking. | medium | A message confirming cancellation with the exact penalty deducted. | - | Penalty fees are determined according to the service providers. | aliaa
| 2.23 | As a User I will get a penalty of cancel booking before the timing depending on the service provider policy. | low | A message confirming cancellation with the exact penalty deducted. | The User decides not to cancel booking, So no deduction is required |  | aliaa
| 2.24 | As a User I want to rate the place I went So that other future users can see this rating. | medium | A message confirming that the rating and review has been posted | User doesn’t rate the place, a relevant error message appears, and rating is unsuccessful. | - | moustafa
| 2.25 | As a User I want to view the history of My Bookings So that I can know what bookings I have done since I joined the website. | low | User booking summary page is viewed. | No booking summary available. Appropriate message is displayed. | - | amr
| 2.26 | As a user , I can post cinema's reviews to be able to add my opinion of the activity. | medium | Detailed reviews are posted |  |  | amr
| 2.27 | As a user , I can post concert's reviews to be able to add my opinion of the activity. | medium | Detailed reviews are posted |  |  | amr
| 2.28 | As a user , I can post escaperoom's reviews to be able to add my opinion of the activity. | medium | Detailed reviews are posted |  |  | amr
| 2.29 | As a user , I can post fight's reviews to be able to add my opinion of the activity. | medium | Detailed reviews are posted |  |  | amr
| 2.3 | As a user , I can post kora's reviews to be able to add my opinion of the activity. | medium | Detailed reviews are posted |  |  | amr
| 2.31 | As a user , I can post malahy's reviews to be able to add my opinion of the activity. | medium | Detailed reviews are posted |  |  | amr
| 2.32 | As a user , I can post race's reviews to be able to add my opinion of the activity. | medium | Detailed reviews are posted |  |  | amr
| 2.33 | As a user , I can post theater's reviews to be able to add my opinion of the activity. | medium | Detailed reviews are posted |  |  | amr
| 2.34 | As a user , I can post trampoline's reviews to be able to add my opinion of the activity. | medium | Detailed reviews are posted |  |  | amr
| 2.35 | As a user, I can view my profile | medium | details about profile are displayed |  |  | nour
Service Provider | 3.1 | As a Service provider I should be able to Sign in So that I can access my account. | High | Service Provider is redirected to the last page he/she was on before log in. | • Unregistered e-mail • Password does not match provided e-mail • User is blocked. | • client,service provider and Admin have the same view. • In all mentioned exceptions, a relevant error message is displayed verifying the exact problem and login is unsuccessful. | youmna
| 3.2 | As a Service provider I should be able to Keep Track of All the Bookings So that I can build statistics and manage bookings. | medium | Booking details are retrieved and viewed. | No bookings exist. Empty page | - | Islam
| 3.3 | As a service provider I want to sign out So that I can leave my page. | low | User is redirected to the directory page | - | - | youmna
| 3.4 | As a Service provider I should be able to update category if cinema | medium | updated info displayed |  |  | rana(backed)-nour(frontend)
| 3.5 | As a Service provider I should be able to update category if concert | medium | updated info displayed |  |  | rana(backed)-nour(frontend)
| 3.6 | As a Service provider I should be able to update category if escaperoom | medium | updated info displayed |  |  | rana(backed)-nour(frontend)
| 3.7 | As a Service provider I should be able to update category if fight | medium | updated info displayed |  |  | rana(backed)-nour(frontend)
| 3.8 | As a Service provider I should be able to update category if kora | medium | updated info displayed |  |  | rana(backed)-nour(frontend)
| 3.9 | As a Service provider I should be able to update category if malahy | medium | updated info displayed |  |  | rana(backed)-nour(frontend)
| 3.1 | As a Service provider I should be able to update category if race | medium | updated info displayed |  |  | rana(backed)-nour(frontend)
| 3.11 | As a Service provider I should be able to update category if theater | medium | updated info displayed |  |  | rana(backed)-nour(frontend)
| 3.12 | As a Service provider I should be able to update category if trampoline | medium | updated info displayed |  |  | rana(backed)-nour(frontend)
| 3.13 | As a Service provider I should be able to Send Offers So that I can motivate the users to book. | medium | A message verifying upload. | Mandatory fields are not filled. Message is displayed | A normal user or visitor can never have access to this page. | rana
| 3.14 | As a Service provider I should be able to update business information. | High | Message confirming update. | Required fields are not sent. Old ones are displayed | A normal user or visitor can never have access to this page. | nour
| 3.15 | As a Service provider I should be able to Post details about my business So that I can modify my business more to the user. | High | A message confirming upload and an email is sent to verify it is posted. | Mandatory fields are not filled. Appropriate message is displayed. | A normal user or visitor can never have access to this page. | amr
| 3.16 | As a Service Provider I should be able to reply to reviews, so that I can thank the customer or defend myself. | medium | A message confirming that the comment is posted. | No body exists. Appropriate message is sent. | - | aliaa
| 3.17 | As a service provoder I want to view all my reviews. | meduim | a detaild info about each review |  |  | aliaa
| 3.18 | As a service provider I should be able to view my profile. | High | information is displayed |  |  | nour
Admin | 4.1 | As an admin I should be able to sign in to the website So that I can access my page. | High | Admin is redirected to the admin page. | • Unregistered e-mail • Password does not match provided e-mail • The username and password doesn't match the admin's profile. | • client,service provider and Admin have the same view. • In all mentioned exceptions, a relevant error message is displayed verifying the exact problem and login is unsuccessful. | youmna
| 4.2 | As an admin I should be able to accept or reject business requests So that I can add new service-providers and new search directory for that new business. | High | Confirmation message is sent. Search directory and service provider account is created. | Missing information. | A business page can never be added to the system unless the admin accepts it. | amr
| 4.3 | As an admin I should be able to suspend a user/block him So that no bad habits are in the website (bad reviews, insulting users, etc.…). | medium | Confirmation message appears and a warning sent to the user. | - | - | aliaa
| 4.4 | As an admin I should be able to unblock user | low | user has free access to the website |  |  | aliaa
| 4.5 | As an admin I should be able to view the users account info So that I can know all information and details about the website users. | High | User information is retrieved and viewed | User does not exist. Appropriate message is shown | - | kareem
| 4.6 | As an admin I should be able to view a list of the users So that I can view the summary overview about my users. | High | A list of all users is retrieved. | No users exist. Error message appears accordingly. | - | sara
| 4.7 | As an admin I should be able to Add business | high |  |  |  | amr
| 4.8 | As an admin I should be able to add new search filter So that I can add a new category to the search filtering option. | Low | filter is added | Search filter already exists. | - | nour
| 4.9 | As an admin I should be able to logout, to leave my acount. | low | reurn to page |  |  | youmna
EXTRA FEATURE | 5.1 | As an admin I want to be able to count the number of users registered in my Website, to be able to make my statstics. | medium | The number of users is retrieved and viewed | No users exist. Error message appears accordingly. |  | All